Document Revision History

(The following table lists revisions made to this document, tracked by publication version.)

| #.# | Sections Modified and Description | Date | Author |
| --- | --- | --- | --- |
| 1.0 | Initial release in Documentum. Legacy BN document 161459. Updated Section 3 references. Added responsibility to the PM During Project Execution in Section 5.3. 136867968* | 3 Aug 2015 | G Gupta |
| 2.0 | Clarification to line items 5.2.5, 5.3.3 and 5.3.11; rebranding 204935292* | 17 March 2020 | J Fredrick, C Stephens |
| 3.0 | Update multiple sections to reflect change to SPM role name | 1 Jan 2026 | M Samir |

Table of Contents

1.0 Purpose	3

2.0 Scope & Applicability	3

3.0 Terms, Definitions, Acronyms	4

4.0 Process Requirements & Instructions	5

4.1 Project Site Lead Primary Responsibilities	5

4.2 Project Planning	5

4.3 Project Execution	6

4.4 Project Financials and Control Measures	6

4.5 Project Closeout	6

5.0 References	7

6.0 Quality Records	7

7.0 Compliance Timeline	7

# Purpose

This document describes the process to ensure that Project Site Leads possess the appropriate knowledge and tools to properly and safely execute the installation of projects in a timely and cost effective manner. Projects that include Augury, BHC3, or ARMS scope are excluded from the applicability of this document.

# Scope & Applicability

The scope of this document covers Type 2 projects handled by the Cordant Services Project Site Leads. Type 2 Projects are defined by the following criteria:

- The project does not contain racks, cabinets, or Factory Acceptance Test (FAT), but does include lumpsum services or onsite subcontractor scopes.

- The project involves existing on-premise software upgrades or scopes that are fully site-executed (such as onsite retrofit or upgrade).

Additionally, the Project Site Lead (PSL) is assigned to Type 1 projects managed by a Project Manager when service activities such as services, subcontractor work, or local material purchases are combined with hardware (HW) or software (SW). In these instances, the PSL is responsible for site supervision and the management of service deliverables.

| Scope/Quote |  |  | Project Type | WBS SAP Responsible Person Assignment |  |
| --- | --- | --- | --- | --- | --- |
| HW | SW | SVC/PLM |  | PM | PSL |
| Yes |  |  | Type-1 | Yes |  |
|  | Yes |  | Type-1 | Yes |  |
| Yes |  | Yes | Type-1 | Yes | Yes |
|  | Yes | Yes | Type-2 |  | Yes |
| Yes | Yes | Yes | Type-1 | Yes | Yes |
|  |  | Yes | Type-2 |  | Yes |

Table 1: Scope-to-WBS Assignment Matrix for SAP Responsibility

# Terms, Definitions, Acronyms

Refer to the Baker Hughes acronym directory for standardized terms, definitions and acronyms.  Terms may be repeated here for convenience; however, in the event of any conflict, the list in this document will take precedence.

- BH: Baker Hughes

- BN: Bently Nevada

- CS: Cordant Solutions

- COF: Cost of Failure

- D&IS: Design & Installation Services

- EKO: External Kick-Off

- FAT: Factory Acceptance Test

- HW: Hardware

- IET: Industrial Energy Technology

- IKO: Internal Kick-Off

- M&S: Maintenance & Support

- OMR: Operational Metadata Repository

- PM: Project Manager

- PO: Purchase Order

- PSL: Project Site Lead

- QMS: Quality Management System

- R3: Review stage/phase in the ITO workflow

- RMA: Return Material Authorization

- SVC: Services

- PL&M: Purchased Labor and Material

- PM: Project Manager

- SW: Software

- WI: Work Instruction

# Process Requirements & Instructions

## Project Site Lead Primary Responsibilities

The Project Site Lead will be responsible for the necessary logistics, design, supervision, execution, and overall customer satisfaction of the Department’s installation projects as assigned by Management.

4.1.1	 APPLICATION OF CORPORATE OBJECTIVES:  Provide a quality system installation for Cordant Solutions Services customers.

4.1.2	 SAFETY:  Ensure all projects are executed safely.  Assume responsibility for own safety.  Monitor site safety (including all Cordant Solutions and subcontractor personnel) during project execution through the use of daily/weekly meetings and audits.

4.1.3	 QUALITY:  Ensure that the quality of the installation is consistent with the standards of Cordant Solutions Services and the customer, including onsite services, subcontractor supervision, site management, and contractual deliverables. Follow the applicable Services and Engineering QMS relevant to the scope of work.

4.1.4	 TIMELINESS:  Ensure the assigned projects/tasks are executed in a timely manner and in accordance with the customer's schedule.

4.1.5	 COST:  Ensure projects are executed in accordance with the cost allocations, which are budgeted, including direct cost and labor hour management.  Anticipate, notify management, and manage accordingly any potential overruns.

## Project Planning

4.2.1 The Service Manager assigns the project to a Project Site Lead (PSL) as part of the R3 Handoff Process. During the R3 Handoff Process, the Service Manager reviews the R3 folder with the assigned PSL and ensures the understanding of Scope, Pricing, Proposal, Contract, Schedule and Logistics.

4.2.2 The PSL proceeds with the process related with the Internal Kickoff Meeting and External Kickoff Meeting, following the applicable IKO QMS and EKO QMS documents as required for the scope of work.

4.2.3 The PSL assumes the role of the “Responsible Person” on SAP. The PSL will ensure accurate Order Booking, Baselining, Forecasting and Scheduling of the required Engineering resources on SAP using the applicable process such as SWOR and/or OTR Setup tool. The PSL is responsible to coordinate with the Fulfilment Managers for scheduling and assigning required field resources for the execution of the project deliverables.

4.2.4 The PSL will perform the required activities for ordering internal software material including M&S, Licenses and subscriptions through the ZPH process; and third-party subcontractor and purchased labor and material (PL&M) through the Sourcing team.

## Project Execution

4.3.1 The PSL is expected to act as the Single Point of Contact for the project and maintain regular communication with the client on the schedule and progress.

Note: In cases where the project is a Type 1, then the Project Manager remains the Single Point of Contact for the project.

4.3.2 All resources involved in the project should be briefed by the PSL on all aspects of the project including the safety risks, scope and deliverables, timelines, and cost.

4.3.3 The PSL is responsible for the supervision, coordination and daily briefing on all internal and external (subcontracted) resources.

4.3.4 The PSL is expected to coordinate and attend regular progress meetings with the client throughout the execution of the project to document the progress, potential issues, support needed, and other aspects of the project which may impact the final deliverables.

4.3.5 The PSL is responsible for conducting and documenting regular safety meetings as per site requirements.

## Project Financials and Control Measures

4.4.1 The PSL is required to provide the Service Manager with progress on the execution and financial forecast dates for the revenue and costs. The PSL is accountable for reviewing and managing the backlog forecasts on SAP while coordinating and aligning with the Service Manager.

4.4.2 The PSL is required to address and resolve issues, delays, escalations related to the quality, schedules / timelines, resources, and cost overruns. The PSL must follow Cost of Failure (CoF) and Return Material Authorization (RMA) Work Instructions. For situations involving revenue forecast and margin erosions, PSL must inform the Service Manager to agree on the corrective actions.

4.4.3 The PSL is expected to process the Revenue Recognition in adherence to the Revenue Recognition guidelines and trigger the Billing milestones through the Business Analysts. PSL is also expected to support in the cash collection process in cases of disputes or escalations.

## Project Closeout

4.5.1 The PSL shall perform a final debriefing interview with the involved Cordant Solutions Services personnel prior to the demobilization from site.  This debriefing should include verification of compliance to scope completed, remaining issues if any, and time allocated as compared to expectations.

4.5.2 The PSL must conduct a closeout meeting with the Customer's Site Contact prior to final demobilization to review the project objectives and deliverables, safety, quality, timeliness and obtain the final Completion Certificate.

4.5.3 The PSL should consolidate the field reports and prepare the final project report within one week of final demobilization and upload to the OMR SharePoint.

4.5.4 The PSL is expected to run a final margin analysis report to compare as sold versus actual on the project.

4.5.5 The PSL may initiate a postmortem review to share lessons learned and process improvement. The “Project Closeout Checklist” may be used for this purpose.

# References

Electronic copies of published QMS documents are available online in the Document Library.

- OTR Field Service Readiness Review(GEMCS-BN_PWI 8.5-004)

- OTR Engineering Process(GEMCS-BN_TP 7.3-001)

- OTR Projects External Kickoff Meeting(BN-OTR-001)

- OTR Projects Internal Kickoff Meeting(BN-OTR-002)

- OTR Services Project Report Standards (GEMCS-BN_FWI 7.5-157635)

# Quality Records

- There are no quality records for this document.

# Compliance Timeline

- The following timeline is expected from all organizations within scope of this document:

- Full compliance to this process upon document publication.