Document Revision History

(The following table lists revisions made to this document, tracked by publication version.)

| #.# | Sections Modified and Description | Date | Author |
| --- | --- | --- | --- |
| 1.0 | Initial release in Documentum. Legacy BN document 161459. Updated Section 3 references. Added responsibility to the PM During Project Execution in Section 5.3. 136867968* | 3 Aug 2015 | G Gupta |
| 2.0 | Clarification to line items 5.2.5, 5.3.3 and 5.3.11; rebranding 204935292* | 17 March 2020 | J Fredrick, C Stephens |

*See Support Central workflow for approval record.

Table of Contents

1.0 Purpose	3

2.0 Scope & Applicability	3

3.0 Terms, Definitions, Acronyms	3

4.0 Process Requirements & Instructions	4

5.0 Responsibilities	4

6.0 References	7

7.0 Quality Records	7

8.0 Compliance Timeline	7

Purpose

This document describes the process to ensure that Site Project Managers possess the appropriate knowledge and tools to properly and safely execute the installation of projects in a timely and cost effective manner.

Scope & Applicability

This process applies to/will be used by all Bently Nevada Services Field Personnel.

Terms, Definitions, Acronyms

Refer to the GE O&G QMS Lexicon for standardized terms, definitions, and acronyms.  Terms may be repeated here for convenience; however, in the event of conflict, the GE O&G QMS Lexicon will take precedence.

- BN- Bently Nevada

- DS- Digital Solutions

- SPM- Site Project Manager

- PO- Purchase Order

Process Requirements & Instructions

- Project – a large undertaking, usually more than $20,000.00 in scope, using multiple disciplines to accomplish the scope, requires Site Project Management, and is properly planned.

- Manager – a person who directs a team.

Responsibilities

5.1	Site Project Manager Primary Responsibilities:

The Site Project Manager will be responsible for the necessary logistics, design, supervision, execution, and overall customer satisfaction of the Department’s installation projects as assigned by Management.

5.1.1	 APPLICATION OF CORPORATE OBJECTIVES:  Provide a quality system installation for Bently Nevada Services customers.

5.1.2	 SAFETY:  Ensure all projects are executed safely.  Assume responsibility for own safety.  Monitor site safety (including all Bently Nevada and sub contract personnel) during project execution through the use of daily/weekly meetings and audits.

5.1.3	 QUALITY:  Ensure that the quality of the installation is consistent with the standards of Bently Nevada Services and the customer, including designs, fabrication, site management, and execution of projects.

5.1.4	 TIMELINESS:  Ensure the assigned projects/tasks are executed in a timely manner and in accordance with the customer's schedule.

5.1.5	 COST:  Ensure projects are executed in accordance with the cost allocations, which are budgeted, including direct cost and labor hour management.  Anticipate, notify management, and accommodate accordingly any potential overruns.

5.1.6 The Site Project Manager may be responsible for generating or obtaining any preliminary Auto-CAD drawings to aid in the proposal of the project to the customer depending on the regional structure.  Check with your Service Manager or Team Lead for clarification.

5.1.7 The Site Project Manager will assist the Service Manager and Commercial Operations (Proposal Specialist) with proposals as required.

5.2 Site Project Manager’s Responsibilities after the receipt of a Purchase Order:

5.2.1 The Service Manager or Team Lead assigns the project to a Site Project Manager (SPM), and informs the Account Manager.

5.2.2 The Service Manager or Team Lead reviews the entire Project Information Package with the SPM and assures understanding of Scope, Proposal, Contract, Schedule and Logistics.

5.2.3 The SPM reviews the hardware and software scope of supply and checks the sales order for accuracy.  If a sales order has not been entered into the R3 System the SPM facilitates the entry of the proper order.

5.2.4 The SPM establishes communication with the Account Manager and Customer within two business days of receipt of the P.O.

5.2.4.1 This allows us to establish a credible relationship with the site contact, and should be used to verify scope and schedule, enabling us to iron out the details and expectations. Remember to thank the customer for the opportunity.

5.2.4.2 It is imperative that this communication is established early to put our customer's mind at ease that we are on top of the project!

5.2.5 Any follow up communications should be executed within the agreed timetable.

5.2.6 The SPM should establish communications with the appropriate local service coordinator to ensure that project resources are scheduled.

5.3 Site Project Manager’s Responsibilities During Project Execution:

5.3.1 The SPM will maintain regular communications with both the Service Manager or Team Lead and the Customer's Site Contact (or as the customer requires).

5.3.2 Discussion should center on work progress, schedule problems, hardware problems, project costs, etc.

5.3.3 If there are problems that may jeopardize our ability to meet scope or schedule, the SPM should contact the Service Manager or Team Lead to escalate.

5.3.4 The SPM should maintain contact with the appropriate Service Manager or Team Lead to give them as much notice for scheduling purposes as possible.

5.3.5 While on site, the SPM will also maintain a daily logbook in accordance with procedure Bently Nevada Services Project On Site Logbook Instructions GEMCS-BN_FWI 7.5-157631

5.3.6 SPM will provide a weekly update to the Service Manager or Team Lead.  The update should include any scheduling conflicts, hardware/software issues, any subcontractor delays or concerns, and a basic overall report of progress.  This will include any potential cost overruns due to changes in scope or schedule.

5.3.7 The SPM is responsible for the supervision of all sub-contracted labor. This including the quality of the installation, the adherence of the contractor to the contract specifications and safety adherence.

5.3.8 The SPM does not have the authority to extend a subcontract past the authorized purchase order (PO) amount, or for a T&M job past the “Do not exceed” amount.  All subcontractor T&M purchase orders must have a “Do not exceed” amount.  A new subcontractor PO will be necessary in order to extend the original PO.  It is the SPMs responsibility to ensure that the subcontractor does not exceed the authorized PO amount.  The Service Manager or Team Lead can authorize an extension to the subcontractor PO for up to 5 business days, while a new subcontractor PO is being generated.

5.3.9 All Bently Nevada Services personnel involved in the project should be briefed by the SPM prior to arriving at site, or when they arrive on site regarding all aspects of the project.  Particular attention should be paid to the estimated time they will be required on site as computed by the Commercial Operations (Proposal Specialist).

5.3.10 The SPM shall engage Bently Nevada Services personnel prior to their leaving a project site to conduct an exit interview.  This debriefing should include verification of compliance to scope completed, remaining issues if any, and time allocated as compared to expectations.

5.3.11 If a Machinery Diagnostics (MDS) team member will provide follow up services, the SPM will arrange for a face-to-face turnover with the customer at the project site if possible.

5.3.12 The SPM must conduct an exit interview with the Customer's Site Contact prior to leaving the site or on completion of the project.  This should take place the day before site implementation activities are completed if possible.  A remote meeting may be acceptable in some situations.  Check with your Service Manager or Team Lead to determine if this is an option.  A summary review of project objectives should be discussed with respect to Safety, Quality, Timeliness and Cost.  It is most appropriate to confirm the customer's expectations regarding delivery of the installation report at this time.

5.3.13 The SPM is responsible for the conducting and documentation of daily and weekly safety meetings while on site.

5.3.14 The SPM is responsible for inventorying hardware and identifying any hardware deficiencies. The SPM is responsible to take corrective action to remedy the deficiencies.

5.3.15 The SPM is responsible to control costs on the project (material and labor) without sacrificing quality.

5.3.16 The SPM is required to provide the Service Manager or Team Lead with written Site Project Manager Reports in accordance with procedure Bently Nevada Services Project Report Standards GEMCS-BN_FWI 7.5-157635

5.3.17 The SPM is required to attend the Customer meetings as required.

5.3.18 The SPM is required to maintain project schedule to assure the meeting of customer’s schedule.

5.3.19 The SPM will drive completion of the TCP before shipment and before closure of all projects.

5.4 Site Project Manager’s Responsibilities During Design Activities:

5.4.1 If applicable, the SPM may be responsible for providing mechanical designs applicable to the installation, which are consistent with Bently Nevada Services and industry best practices and follow the standard design approval process.  Check with your Service Manager or Team Lead to determine if your region has the SPM performing mechanical designs.

5.4.2 If applicable, the SPM may be responsible to have the mechanical designs reviewed with the Service Manager or Team Lead and the Customer prior to implementation.

5.5 Post Project Completion Responsibilities:

5.5.1 The SPM should prepare the final report as quickly as possible to allow for project closure and invoicing (within 10 days of project completion).

5.5.2 The SPM may participate in a Post-Mortem with the following attendees: Service Manager or Team Lead, Account Manager, Commercial Operations (Proposal Specialist), and Regional Service Director.

5.5.3 The post-mortem will be used to dissect how we did on the project

5.5.4 Did we meet the customer's expectations?  Why, or Why Not

5.5.5 Did we meet our expectations/margin?  Why, or Why Not

5.5.6 What can we do better? / How can we apply what we learned?

5.5.7 A follow up call to the customer from the Service Manager or Team Lead and SPM, coordinated with the Account Manager, on how the installed systems are meeting their needs is advised.

References

Electronic copies of published QMS documents are available online in the Document Library.

Including:

- Bently Nevada Services Project On Site Logbook Instructions GEMCS-BN_FWI 7.5-157631

- Bently Nevada Services Project Report Standards GEMCS-BN_FWI 7.5-157635

- Technical Regulations and Standards BHGE-QUA-OGQ-009

Quality Records

The following records produced by this procedure are considered Quality Records and shall be maintained and controlled according to the applicable BH requirements.

- There are no quality records for this document.

Compliance Timeline

- The following timeline is expected from all organizations within scope of this document:

- Full compliance to this process upon document publication.

|  | Baker Hughes Quality Management System |
| --- | --- |
| Title: | BN Services Site Project Manager Responsibilities |
| Reference: | GEMCS-BN_FP 7.5-161459 |
| Revision: | 2.0 |
| Application Date: | <applicationdate> |
| Expiration Date: | <expirationdate> |
| Author: | <text1> |
| External References: |  |